# Product Brief: Senior Living AI Modernization & Commercialization Discovery

# Product Overview

Product Name: Senior Living AI Modernization & Commercialization Discovery

Target Launch: Discovery engagement timeline TBD; initial findings expected within first 6-8 weeks

Product Owner: Chief Executive Officer / Innovation Sponsor

Stakeholders: Executive Leadership, Facility Operations, Clinical/Care Leadership, Workforce Management, IT Operations, Finance, Compliance, Resident Experience, Family Engagement, Facility Administrators

# Vision Statement

Create a structured modernization and innovation discovery program that helps a distributed senior living organization identify where AI, automation, existing SaaS capabilities, and potential new software products can improve operations, reduce cost, enhance resident and employee experience, and create new revenue streams beyond facility operations.

# Problem Statement

Evergreen Living Services operates a large, distributed network of elder care and assisted living facilities, many of which are located in rural or connectivity-constrained environments. Historically, limited connectivity, uneven technology adoption, and a lean IT organization have slowed modernization efforts and prevented the organization from pursuing more advanced digital and AI-enabled opportunities.

As connectivity improves and a new CEO establishes a stronger innovation mandate, the organization has growing interest in understanding how modern technology can improve operations and potentially create new sources of revenue. However, leadership does not yet have a clear view of which opportunities are highest value, which should be solved through existing SaaS platforms, which may require custom development, and which could become licensable products for other industries.

Today, many core business processes remain manual, fragmented, or only partially digitized. Key issues include:

Connectivity-Constrained Operations: Some facilities operate in rural locations with inconsistent Wi-Fi or network reliability, limiting adoption of digital workflows

Manual Care Documentation: Resident care notes and observations are often captured on paper and later entered into systems, creating delays, duplicate work, and incomplete visibility

Workforce Instability: High employee turnover, staffing shortages, no-shows, and overtime create significant cost pressure and operational risk

Fragmented Technology Landscape: Existing SaaS tools support parts of the business, but leadership lacks a clear understanding of where current platforms are underused, where gaps exist, and where modernization investment would create value

Manual Visitor and Facility Access Processes: Visitor check-in, identity validation, guest tracking, and security workflows are still heavily manual and administratively burdensome

Limited Internal Product Engineering Capability: The IT team is focused primarily on infrastructure, network support, SaaS administration, compliance, and troubleshooting rather than custom product development

Unclear Commercialization Opportunity: Leadership believes some operational problems may represent broader market opportunities, but does not yet know which problems are unique, which are common across industries, what the addressable markets may be, or whether any solution should be licensed externally

This leads to:

Increased overtime and staffing-related cost leakage

Administrative burden for caregivers and facility teams

Delayed or incomplete visibility into resident care activity

Inconsistent operating practices across facilities

Limited confidence in where to invest modernization dollars

Difficulty distinguishing build, buy, partner, and process-change opportunities

Missed opportunities to turn internal operational insight into marketable products or services

# Target Users

## Executive Personas

1. Chief Executive Officer / Innovation Sponsor

Needs: Clear view of modernization opportunities, AI-enabled growth potential, and new revenue possibilities

Goals: Improve operating performance, diversify revenue, and identify where technology can create strategic advantage

Pain Points: Unclear investment priorities, limited internal technical capacity, uncertainty about which ideas are commercially viable

2. Chief Financial Officer / Finance Leader

Needs: ROI visibility, cost-reduction opportunities, investment prioritization, and business case clarity

Goals: Reduce overtime and operating leakage while funding the right modernization opportunities

Pain Points: Difficulty quantifying operational waste, unclear payback periods, limited confidence in technology investment decisions

## Operations Personas

1. Facility Administrator

Needs: Better staffing visibility, simpler visitor management, more consistent facility workflows, and tools that work despite connectivity challenges

Goals: Run facilities safely, efficiently, and consistently while reducing administrative burden

Pain Points: Manual processes, staffing gaps, visitor tracking overhead, inconsistent adoption of technology across locations

2. Workforce Management / HR Leader

Needs: Better visibility into staffing demand, turnover drivers, overtime risk, and schedule gaps

Goals: Reduce turnover, improve coverage, minimize overtime, and stabilize the workforce

Pain Points: Reactive staffing decisions, high replacement costs, inconsistent attendance, and limited predictive insight

## Care & Experience Personas

1. Caregiver / Facility Worker

Needs: Simple ways to document care activity, access relevant resident information, and reduce duplicate administrative work

Goals: Spend more time with residents and less time on paperwork

Pain Points: Paper-based notes, delayed data entry, disconnected systems, and limited access to digital tools during daily work

2. Resident Experience / Family Engagement Leader

Needs: Better visibility into resident care activity, family communication opportunities, and experience improvement areas

Goals: Improve resident and family confidence, transparency, and satisfaction

Pain Points: Inconsistent information flow, delayed updates, and limited ability to turn operational data into resident experience improvements

## Technology & Compliance Personas

1. IT Operations Leader

Needs: A practical modernization roadmap that accounts for existing systems, connectivity constraints, security, and limited internal engineering capacity

Goals: Support innovation without creating unmanageable technical debt or unsupported custom tools

Pain Points: Lean team, fragmented SaaS environment, rural connectivity constraints, and unclear ownership of new technology capabilities

2. Compliance / Risk Leader

Needs: Safe, auditable, and compliant approaches to AI, resident data, workforce data, visitor data, and care documentation

Goals: Enable modernization while protecting residents, employees, and the organization

Pain Points: Privacy risks, inconsistent documentation, regulatory obligations, and uncertainty around AI governance

# Success Metrics

## Discovery & Alignment

Target: Executive alignment on top modernization and commercialization opportunity areas

Target: Clear classification of opportunities by process change, SaaS optimization, AI enablement, custom build, partner, or acquisition

Target: Prioritized roadmap across short-, medium-, and long-term horizons

Measure: Executive workshop outcomes, opportunity backlog quality, decision alignment, roadmap approval

## Operational Modernization Potential

Target: Identification of high-value opportunities to reduce overtime, staffing inefficiency, documentation burden, and manual visitor management effort

Target: Defined business cases for near-term quick wins within 0-6 months

Target: Improved understanding of existing SaaS utilization and modernization gaps

Measure: ROI estimates, operational baseline metrics, SaaS capability assessment, process improvement recommendations

## AI & Automation Readiness

Target: Clear view of where AI can create measurable operational value

Target: Assessment of data readiness, connectivity constraints, compliance needs, and change management requirements

Target: Prioritized AI use cases with feasibility and risk scoring

Measure: AI opportunity scorecards, readiness assessment, risk review, stakeholder validation

## Commercialization Potential

Target: Identification of product concepts that may be licensable beyond Evergreen Living Services

Target: Addressable market and competitive landscape analysis for highest-potential concepts

Target: Recommendation on whether to build, buy, partner, acquire, or defer

Measure: Market sizing, product concept briefs, commercialization recommendations, executive investment decisions

# Business Value

## Operational Impact

Reduce administrative burden in facilities by identifying opportunities to digitize or automate manual processes

Improve staffing efficiency and reduce avoidable overtime through better visibility and decision support

Increase consistency across facilities while accounting for rural and connectivity-constrained realities

Improve care documentation timeliness, visibility, and operational reliability

Reduce friction for facility administrators, caregivers, visitors, residents, and families

## Financial Impact

Identify near-term cost savings from overtime reduction, improved staffing alignment, process automation, and better SaaS utilization

Create investment clarity by comparing the ROI of process change, SaaS optimization, automation, AI enablement, and custom development

Reduce risk of unfocused technology spend by prioritizing opportunities against measurable business value

Establish a decision framework for longer-term software product investment, acquisition, or commercialization

## Strategic Value

Create a modernization roadmap that addresses immediate operational needs while supporting longer-term transformation

Help leadership understand how AI is changing the software and SaaS landscape relevant to senior living operations

Identify whether internal operational challenges can become differentiated product opportunities in adjacent markets

Build a foundation for future digital product thinking, AI governance, and technology-enabled revenue diversification

Position the organization as an innovation leader in senior living and distributed care operations

# Technical Considerations

Assessment of current facility connectivity, rural network limitations, offline workflows, and reliability requirements

Integration considerations across EMR/EHR, workforce scheduling, payroll, HRIS, visitor management, learning management, and reporting tools

Evaluation of data quality, data accessibility, system interoperability, and reporting maturity

Security and privacy requirements for resident data, employee data, visitor data, and operational data

AI governance considerations including human review, explainability, auditability, privacy, and operational control

Support model considerations given limited internal engineering capacity

Evaluation of build, buy, partner, and acquisition models for future product development

Scalability requirements for solutions used across multiple facilities with inconsistent technical environments

# Constraints & Dependencies

Lean IT organization with limited internal product engineering and data engineering capacity

Connectivity constraints in rural and remote facility locations

Existing SaaS platforms may have underused capabilities or integration limitations

Operational workflows vary across facilities and may require standardization before automation

Resident care, workforce, and visitor workflows may involve sensitive or regulated data

Leadership must balance quick wins, multi-year transformation, and long-term commercialization bets

Future custom development may depend on consulting partners, engineering vendors, acquisition, or new internal capability building

Commercialization decisions require market research, competitive analysis, legal review, and go-to-market planning

# Risks

Over-Scoping the Discovery - The opportunity space may become too broad without clear prioritization criteria

Connectivity Limitations - Rural facilities may not support certain digital or AI-enabled workflows without infrastructure investment

Data Readiness Gaps - Incomplete, inconsistent, or inaccessible data may limit AI feasibility and ROI confidence

Operational Adoption Challenges - Facility teams may resist new workflows if solutions increase complexity or do not reflect day-to-day realities

Compliance and Privacy Risk - Resident, employee, and visitor data must be handled safely, especially in AI-enabled use cases

Build-Vs-Buy Misalignment - Leadership may overinvest in custom solutions where SaaS capabilities already exist or underinvest where differentiation is possible

Commercialization Uncertainty - Internal problems may not translate into viable external products without clear market demand, differentiation, and distribution strategy

Limited Internal Technical Capacity - The organization may need external partners or acquisition to build and sustain custom products

# Open Questions

Which operational pain points create the greatest financial impact today?

Which current SaaS capabilities are underused and could deliver value without custom development?

Which workflows are most constrained by connectivity, and which can be designed for offline or intermittent use?

Where can AI materially improve staffing, care documentation, visitor management, compliance, or resident experience?

Which opportunities should be solved through process improvement, existing SaaS platforms, automation, custom software, partnership, or acquisition?

Which internal problems are common across adjacent industries and could support licensable product concepts?

What addressable markets should be explored for potential commercialization?

What investment horizon should leadership prioritize across quick wins, transformation, and new revenue creation?

What internal capabilities are required to sustain modernization and product development over time?

# Compliance & Privacy

Resident care data must be handled in accordance with applicable healthcare, privacy, and senior living regulatory requirements

Employee workforce data must be protected and governed appropriately

Visitor identity and access data must be managed securely with appropriate retention policies

AI-enabled recommendations or automation must include human oversight where resident care, staffing, compliance, or safety are affected

Audit logging, access controls, and data governance should be included in any future solution design

Commercialization concepts must account for privacy, data rights, liability, and regulatory differences across target industries

Last Updated: June 1, 2026

Status: Draft - Pending stakeholder workshop and opportunity discovery